## Sheet2
DEFECT LOG TRACKER ( TBS - CRM )
Project Name | Thebusstand.com V_0.1
Project Manager
Phase | Testing
Module | Testing/CRM - AD
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution.This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No | Date Created | Created By | Defect Name/Issue Description | Steps | Expected Result | Actual Result | Assisgned To | Life Cycle Phase | Severity | Priority | Assigned Date | Status | Updated Status By Dev Team | Updated Status Date | Remarks by Dev | Remark Date | Reviews by Tester | Testcase_Screenshot
1 | 2024-08-27 | Sakthi N | Click the Add Ads button to bring up the pop-up screen in the advertisement module in order to create a new advertisement. The content won't be modified if the status is changed from draft mode to active; instead, a new advertisement will be made utilizing the updated status. | 1) Open the URL link of CRM in the browser | User should be able to open the URL link of CRM in the browser | User is able to open the URL link of CRM in the browser | Manoj P | Testing | Major | High |  | New
|  |  |  | 2) Login with the valid credentials in the login screen | User should be able to login with the valid credentials in the login | User is able to login with the valid credentials in the login screen
|  |  |  | 3) Navigate to the Advertisement module | User should be able to navigate to the Advertisement module | User is able to navigate the Advertisement module
|  |  |  | 4) Click Add Ads button | User should be able to click the Add Adst button in the screen | User is able to click the Add Ads button in the screen
|  |  |  | 5) The add Ads pop up screen displays in the screen | The pop up text box displays, user should be able to add all the required input details in the textboxes | The pop up text box is displaying in the screen and user is able to add all the required input details in the textboxes
|  |  |  | 6) The advertising adds input fields to the Add Ads pop-up screen. If the status is set to draft mode and then changed to active, the content will not be altered; instead, a new ad will be created using the updated status. | The status of the advertisement creation screen can be updated by the owner from his log in screen, reflecting the alteration in the same screen. | The status of the advertisment creation screen is not being updated in the same screen ,though the owner make some changes ,instead it is being displayed in the new screen
2 | 2024-08-27 | Sakthi N | The editing flow in the advertisement module is completely incorrect if any changes are made and an new advertisement is created. | 1) Click Add Ads button | User should be able to click the Add Adst button in the screen | User is able to click the Add Ads button in the screen | Manoj P | Testing | Major | High |  | New
|  |  |  | 2) The add Ads pop up screen displays in the screen | The pop up text box displays, user should be able to add all the required input details in the textboxes | The pop up text box is displaying in the screen and user is able to add all the required input details in the textboxes
|  |  |  | 3) If the add ads screen is altered, a new advertising will be made; if not, the video will be removed. | If there is any thing to be updated , should be updated in same one | when tha changes are made its not getting updated in same one
3 | 2024-08-27 | Sakthi N | The Advertisement video Input box in the Advertisement module's Add ADS Button section accepts all image formats. However, it only supports files in the gif format. hence the web is also reflecting the same image format given in the CRM screen | 1) Click Add Ads button | User should be able to click the Add Adst button in the screen | User is able to click the Add Ads button in the screen | Manoj P | Testing | Major | High |  | New
|  |  |  | 2) The add Ads pop up screen displays in the screen | The pop up text box displays, user should be able to add all the required input details in the textboxes | The pop up text box is displaying in the screen and user is able to add all the required input details in the textboxes
|  |  |  | 3) The screen that creates advertisements accepts all picture formats. However, it only supports the GIF format. | The screen that creates advertisements should only accept the gif format. | Not only does the screen that generates advertisements support the GIF format.It accepts the picture format as well.