## Defect_Log_Tracker
DEFECT LOG TRACKER (WEB)
Project Name | thebusstand.com (Ver_1.0)
Project Manager
Phase | Testing
Module
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution.This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No | Date Created | Created By | Defect Name/Issue Description | Steps | Expected Result | Actual Result | Assisgned To | Life Cycle Phase | Severity | Priority | Assigned Date | Status | Updated Status By Dev Team | Updated Status Date | Remarks by Dev | Remark Date | Reviews by Tester | Testcase_Screenshot
1 | 27/08/2024 | Angel Priya A | Trending Offers - Adding a new promotion in the CRM promotion module, only 7 cards are displayed in the trending offers section in web page; the other cards are not shown | 1) Open the URL of the CRM in the browser | User should be able to open the URL of thebusstand.com in the browser | User able to open the URL of thebusstand.com in the browser | Manoj P | Testing | Major | Medium |  | New | Open
|  |  |  | 2) Login to the CRM screen and navigate to the Promotions page | User should be able to login to the CRM screen and navigate to the promotion page | User able to login to the CRM screen and navigate to the promotion page
|  |  |  | 3) Click the "Add new promotion" button | User should be able to click the "Add new promotion" button | User is able to click the "Add new promotion" button
|  |  |  | 4) Add new promotion in the popup screen | Users should be able to add new promotions in the popup screen | User is able to be able to add new promotions in the popup screen
|  |  |  | 5) When users click the 'Next' button, all cards are displayed in the Trending Offers section on the webpage | Click the next button all offers cards should be displayed on the webpage. | Adding a new promotion in the CRM promotion module,only 7 cards are displayed in the trending offers section in web page; the other cards are not shown
2 | 27/08/2024 | Angel Priya A | Trending Offers - Excessive space is appearing in the Trending Offers card. | 1) Open the URL of thebusstand.com in the browser | User should be able to open the URL of thebusstand.com in the browser | User able to open the URL of thebusstand.com in the browser | Manoj P | Testing | Major | Low |  | New | Open
|  |  |  | 2) Click the 'Next' button on the Trending Offers card on the webpage | Users should be able to click the 'Next' button on the Trending Offers card on the webpage | User able to click the 'Next' button on the Trending Offers card on the webpage
|  |  |  | 3) Excessive space is being displayed in the card | The offers cards should be fully visible in the Trending Offers section. | Excessive space is appearing in the Trending Offers card.
3 | 27/08/2024 | Angel Priya A | Trending Offers -The offers card image alignment is incorrect | 1) Open the URL for the CRM promotion module in the browser | User should be able to open the URL of CRM promotion module in the browser | User able to open the URL of CRM promotion module in the browser | Manoj P | Testing | Minor | High |  | New | Open
|  |  |  | 2) All Trending Offers cards should be displayed correctly when the 'Next' button is clicked." | All trending offers card image should be displayed correctly | The offers card image alignment is incorrect