## Major_Defect _Log_Tracker
DEFECT LOG TRACKER (Android_TBS)
Project Name | thebusstand.com (Ver_2.1)
Project Manager
Phase | Andriod Testing - Major Bugs
Module | Home Screen/Dashboard/Bookings/Help/Profile
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution.This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Major Bugs |  |  |  | TBS_MobView_Major_Defect_Doc_Ver_2.1
Defect No | Date Created | Defect Name/Issue Description | Assigned Date | Updated Status By Testing Team | Updated Status By Dev Team | Fixed Status Date | Remarks by Dev | Remark Date | Reviews by Tester
1 | 26/09/2024 | Home Screen - When the user click the back button on the device it will be navigate to App logo screen again it's not redirect to home page. | 28/09/2024 | New
2 | 26/09/2024 | Home Screen -Recently searched “Book” button navigated to “Journey details” page instead of “Bus Type Details” page. | 28/09/2024 | New
3 | 26/09/2024 | Dashboard - When user select "view more" on the card, the application closes. When you click "View More," a pop-up window should be appear. | 28/09/2024 | New
4 | 26/09/2024 | Dashboard - On the dashboard, click the luxury coach filter, then select the sort filter. The luxury coach filter should be selected, but it is not being selected as per the design. | 28/09/2024 | New
5 | 26/09/2024 | Dashbaord - Select the luxury bus on the bus type details page. The luxury bus screen should be displayed, but the regular bus page is shown insteade is display. | 28/09/2024 | New
6 | 26/09/2024 | Dashboard - Click the backbutton in the dashboard it should navigates "Bus Details Page" instead it navigates low price scanning card. | 28/09/2024 | New
7 | 26/09/2024 | Popular Filters - While clicking the search bar,the keyboard popup will be open the screen should not be hide. | 28/09/2024 | New
8 | 26/09/2024 | Ticket Details - When users click the home button,it redirect the bus details type page | 28/09/2024 | New
9 | 26/09/2024 | Booking Histrory - The download button is not working, and the popup page is not displayed. | 28/09/2024 | New
10 | 26/09/2024 | Verify OTP Close Symbol Functionality - Click the close icon, the login page should open, but it opens the previous page instead. | 28/09/2024 | New
11 | 27/09/2024 | Traveller Details - Add new passenger checkbox is not working, when users click the check box it should working | 28/09/2024 | New
12 | 27/09/2024 | Help and Support - While clicking the message text box ,the keyboard popup will be open the screen should not be hide. | 28/09/2024 | New